# Project Schedule / Gantt Chart Plan

## 1.0 Initiation Phase (Oct 10 – Oct 18)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.1.1 | Form project team | Oct 10 – Oct 11 | 2 days |
| 1.1.2 | Identify stakeholders | Oct 11 – Oct 12 | 2 days |
| 1.1.3 | Define purpose & scope | Oct 12 – Oct 14 | 3 days |
| 1.1.4 | Develop project charter | Oct 14 – Oct 17 | 4 days |
| 1.1.5 | Review & approve charter | Oct 17 – Oct 18 | 2 days |

## 2.0 Planning Phase (Oct 19 – Nov 3)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.2.1 | Communication Plan | Oct 19 – Oct 21 | 3 days |
| 1.2.2 | Risk Management Plan | Oct 21 – Oct 23 | 3 days |
| 1.2.3 | Quality Management Plan | Oct 23 – Oct 24 | 2 days |
| 1.2.4 | Scope Management Plan | Oct 24 – Oct 26 | 3 days |
| 1.2.5 | Cost Management Plan | Oct 26 – Oct 27 | 2 days |
| 1.2.6 | Resource Management Plan | Oct 27 – Oct 29 | 3 days |
| 1.2.7 | WBS Development | Oct 29 – Oct 31 | 3 days |
| 1.2.8 | Create Project Schedule | Oct 31 – Nov 2 | 3 days |
| 1.2.9 | Planning Review & Approval | Nov 2 – Nov 3 | 2 days |

## 3.0 Execution Phase (Nov 4 – Dec 4)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.3.1 | Gather mock dataset | Nov 4 – Nov 6 | 3 days |
| 1.3.2 | Clean dataset | Nov 6 – Nov 10 | 5 days |
| 1.3.3 | Energy analysis | Nov 10 – Nov 14 | 5 days |
| 1.3.4 | Dashboard development | Nov 14 – Nov 23 | 10 days |
| 1.3.5 | Dashboard validation | Nov 23 – Nov 26 | 4 days |
| 1.3.6 | Sustainability recommendations | Nov 26 – Nov 30 | 5 days |
| 1.3.7 | Develop educational campaign | Nov 30 – Dec 4 | 5 days |

## 4.0 Monitoring & Controlling (Oct 10 – Dec 15)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.4.1 | Weekly meetings | Oct 10 – Dec 15 | Ongoing |
| 1.4.2 | Track progress | Oct 19 – Dec 15 | Ongoing |
| 1.4.3 | Update risk log | Oct 21 – Dec 15 | Ongoing |
| 1.4.4 | Documentation QA | Oct 21 – Dec 10 | Ongoing |
| 1.4.5 | Dashboard corrections | Nov 23 – Dec 10 | 18 days |
| 1.4.6 | Version control | Entire Project | Ongoing |

## 5.0 Closing Phase (Dec 4 – Dec 15)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.5.1 | Final report | Dec 4 – Dec 10 | 7 days |
| 1.5.2 | Final presentation development | Dec 10 – Dec 13 | 4 days |
| 1.5.3 | Final team review | Dec 13 – Dec 14 | 2 days |
| 1.5.4 | Submission of project | Dec 15 – Dec 15 | 1 day |
| 1.5.5 | Project close-out reflection | Dec 15 – Dec 15 | 1 day |