# Final Project Report

Project: Smart Campus Energy Management System
Team: EcoVision

Subject: 301- Project Management Analytics

Professor:  Dr. Ali Alsarif

Group Members:

Pushp Chandrasinh Rathava(0867974)

Dev Sureshbhai Patel(0873768)

Sunny (0877893)

INDEX

| Sr.no | Content | Page no. |
| --- | --- | --- |
| 01 | Communication Plan | 3 |
| 02 | Risk Management Plan | 5 |
| 03 | Quality Management Plan | 7 |
| 04 | Scope Management Plan | 11 |
| 05 | Cost Management Plan | 13 |
| 06 | Resource Management Plan | 16 |
| 07 | Work Breakdown Structure (WBS) | 19 |
| 08 | Project Schedule / Gantt Chart Plan | 22 |
| 09 | Solution Roadmap (Basecamp! Style) | 25 |

# Communication Plan

## 1. Purpose of the Communication Plan

The purpose of this Communication Plan is to ensure that all project team members share updates, decisions, documents, and progress efficiently. This structured communication framework helps maintain project alignment, avoid delays, and support timely decision‑making throughout the project lifecycle.

## 2. Communication Objectives

• Provide clear and timely updates to all team members.

• Ensure alignment on scope, tasks, and deliverables.

• Maintain accurate and accessible documentation.

• Enable fast and effective decision-making.

• Avoid miscommunication or duplicated work.

## 3. Stakeholder Communication Requirements

| Stakeholder | Information Needed | Frequency | Mode of Communication | Owner |
| --- | --- | --- | --- | --- |
| Pushp (Project Manager) | Task progress, risks, dashboard updates | 2–3 times/week | WhatsApp, in-person, Google Docs | Dev + Sunny |
| Dev (Dashboard Developer) | Dataset updates, requirements, documentation updates | Daily / As needed | WhatsApp, Google Drive, Meetings | Pushp + Sunny |
| Sunny (Documentation Lead) | Task progress, project decisions, screenshots | 2–3 times/week | WhatsApp, Shared Docs, Meetings | Pushp + Dev |

## 4. Meeting Schedule

| Meeting Type | Purpose | Frequency | Format | Participants |
| --- | --- | --- | --- | --- |
| Team Weekly Meeting | Review progress, share updates, identify issues | Weekly (Every Sunday) | In-person or Online | Entire Team |
| Task Review Meeting | Check specific deliverables | Twice a week | WhatsApp Call / Google Meet | Team Member + PM |
| Ad-hoc Meetings | Urgent issues, quick clarifications | As needed | WhatsApp Chat / Call | Relevant Members |

## 5. Communication Tools

• WhatsApp — quick updates, reminders.

• Google Drive — storing documentation and datasets.

• Google Docs / Sheets — collaborative editing.

• Tableau / Power BI — dashboard development.

• Email — formal submissions.

## 6. Communication Escalation Path

If an issue is not resolved within 24 hours:

1. Team member notifies the Project Manager (Pushp).

2. If still unresolved → a group meeting is scheduled.

3. All escalated issues must be documented in the project log.

## 7. Communication Rules & Guidelines

• All documents must be saved in the shared Google Drive folder.

• Team members must update progress every 48 hours.

• Any delays must be communicated immediately to the team.

• Sunny must record meeting notes for weekly meetings.

• Dashboard changes must be communicated before finalizing.

# Risk Management Plan

## 1. Purpose of the Risk Plan

The purpose of this Risk Management Plan is to identify potential risks that may impact the project and outline strategies to monitor, reduce, and manage these risks throughout the project lifecycle. This helps ensure the project stays on schedule, maintains quality, and avoids preventable issues.

## 2. Risk Categories

• Technical Risks

• Data Risks

• Resource & Team Risks

• Time/Schedule Risks

• Documentation Risks

• Tool/Software Risks

## 3. Risk Register

| Risk ID | Risk Description | Category | Probability | Impact | Mitigation Strategy | Response Plan |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Dataset may not match real campus energy use | Data | Medium | Medium | Use mock datasets with realistic values | Adjust analysis; document assumptions clearly |
| R2 | Compatibility issues with Tableau/Power BI | Technical | Low | Medium | Keep software updated; use backup tools | Switch to Power BI if Tableau crashes |
| R3 | Workload imbalance or member unavailable | Resource | Medium | High | Define roles in WBS, cross-train team | Reassign tasks to available members |
| R4 | Project delays due to academic deadlines | Schedule | Medium | High | Create weekly internal deadlines | Adjust task priorities; increase meetings |
| R5 | Miscommunication about deliverables | Communication | Medium | Medium | Use communication plan; frequent updates | Clarify decisions and document changes |
| R6 | Missing documents or version issues | Documentation | Medium | Medium | Use shared Google Drive | Restore backups; recreate if needed |
| R7 | Data not connecting to dashboard | Technical | Low | High | Test early; use sample files | Simplify dataset or use CSV |
| R8 | Low quality analysis or visuals | Quality | Medium | High | Peer review dashboards; early feedback | Fix dashboards before submission |
| R9 | Student availability conflicts | Resource | Medium | Medium | Plan ahead; share schedules early | Adjust meetings; reassign tasks |

## 4. Risk Analysis Summary

Highest Impact Risks:

• R3 – Team availability issues

• R4 – Timeline delays

• R8 – Dashboard/analysis quality issues

Highest Probability Risks:

• R5 – Miscommunication

• R6 – Documentation/version issues

• R1 – Dataset realism issues

## 5. Risk Monitoring & Control Plan

• Weekly review of risks during team meetings.

• Update the risk register whenever a new risk is identified.

• All updates must be documented in the shared Google Drive.

• Only the Project Manager (Pushp) may update the risk status.

# Quality Management Plan

## 1. Purpose of the Quality Plan

The purpose of this Quality Management Plan is to define the quality standards, acceptance criteria, tools, and processes required to ensure the Smart Campus Energy Management System project delivers accurate data analysis, professional dashboards, and clear, consistent documentation throughout the project lifecycle.

## 2. Quality Objectives

• Provide accurate and realistic energy analysis using mock data.

• Create professional, readable, insight-driven dashboards.

• Deliver clear and complete documentation for all project phases.

• Ensure consistency across all team deliverables.

• Maintain proper formatting, grammar, and structure for submission.

## 3. Quality Standards to Follow

### A. Data Quality Standards

• Data must be clean (no duplicates, missing values, or errors).

• All units (kWh, cost, etc.) must be consistent.

• All assumptions must be clearly documented.

• All data sources must be cited correctly.

### B. Dashboard Quality Standards

• Use appropriate chart types (line, bar, map, pie only if necessary).

• Each dashboard must include a clear title.

• All visualizations must have clear labels and legends.

• Color schemes must be consistent across dashboards.

• Include helpful annotations or insights where needed.

• Avoid clutter, overlapping visuals, or unreadable formatting.

• Each dashboard must include 3–5 key findings or insights.

### C. Documentation Quality Standards

• No spelling or grammar mistakes.

• Use a professional academic tone.

• Use APA or required project formatting.

• All required sections must be complete and consistent.

• File naming conventions must be followed (e.g., TeamEcoVision_FinalReport_v1.pdf).

### D. Presentation Quality Standards

• Clean layout with a logical flow.

• Clear storyline that connects problem → analysis → solution.

• Each team member must participate during presentation.

• Include key insights, dashboard screenshots, and recommendations.

## 4. Roles & Quality Responsibilities

| Team Member | Quality Responsibilities |
| --- | --- |
| Pushp (Project Manager) | Validate analysis accuracy, review dashboards, approve all final files. |
| Dev (Dashboard Developer) | Ensure dashboard quality, correct formulas, accurate charts, and realistic data. |
| Sunny (Documentation Lead) | Proofread documentation, ensure formatting, grammar, and alignment with charter. |

## 5. Quality Assurance Activities (QA)

• Weekly review of dashboards and visuals.

• Dataset checks before visualization development.

• Team walkthrough of the Work Breakdown Structure and schedule.

• Peer review of documents before final submission.

## 6. Quality Control Activities (QC)

• Check dashboards for errors, clarity, and correct data connections.

• Validate calculations such as energy usage, savings, and ROI.

• Ensure formatting consistency across all documents.

• Review project plan and final report for alignment with charter.

## 7. Acceptance Criteria

Dashboard Acceptance Criteria:

• Minimum 3 dashboards included in final submission.

• Each dashboard must show at least 2 meaningful insights.

• All datasets must connect correctly to visualizations.

• No visual errors, missing fields, or broken charts.

Documentation Acceptance Criteria:

• All required project management plans included.

• Documents must be free of spelling and grammar issues.

• Documentation must be clear, structured, and professional.

• Final content must match project charter scope.

Final Report & Presentation Acceptance Criteria:

• Report includes findings, screenshots, and recommendations.

• Slides must be clean, consistent, and logically organized.

• Presentation must stay within the time limit.

• Team members must demonsrate full understanding during Q&A.

# Scope Management Plan

## 1. Purpose of the Scope Plan

The purpose of this Scope Management Plan is to clearly define the boundaries of the Smart Campus Energy Management System (SCEMS) project. This ensures the project team remains focused on approved deliverables, avoids scope creep, and completes all requirements within academic deadlines.

## 2. Project Scope Statement

### IN SCOPE (What the project WILL include)

• Collection and cleaning of mock IoT energy consumption data.

• Data analysis to identify energy usage patterns and inefficiencies.

• Designing interactive dashboards using Tableau/Power BI.

• Calculating simulated energy cost savings and ROI.

• Creating sustainability recommendations for students and staff.

• Complete project documentation (Risk Plan, Communication Plan, WBS, Quality Plan, etc.).

• Final project presentation and summary report.

• Educational campaign ideas (posters, tips, awareness messages).

### OUT OF SCOPE (What the project WILL NOT include)

• Installing real IoT sensors or smart meters on campus.

• Integrating with St. Clair’s real Building Management System (BMS).

• Development of a live mobile app.

• Real-time streaming of actual campus data.

• Long-term maintenance after project submission.

• Any construction, electrical work, or hardware installation.

## 3. Major Deliverables

| Deliverable | Description |
| --- | --- |
| Dataset & Analysis Report | Cleaned mock data, trends, insights, and calculations. |
| Smart Energy Dashboards | Visualizations showing usage trends, peak times, and simulated savings. |
| Documentation Package | All PM plans (risk, quality, communication, stakeholder, scope, cost, etc.). |
| Educational Campaign Plan | Posters, awareness messages, sustainability tips. |
| Final Presentation | Summary of insights, dashboards, and recommendations. |

## 4. Work Breakdown Structure (WBS) – Summary Level

• Initiation – Finalize charter, identify stakeholders.

• Planning – Communication, risk, scope, quality, cost, resource plans; WBS and schedule.

• Execution – Dataset collection and cleaning, dashboard development, analysis, campaign planning.

• Monitoring & Controlling – Weekly meetings, dashboard reviews, updates to risks and schedule.

• Closing – Final report, final presentation, submission.

## 5. Scope Verification

• Review all deliverables against the project charter.

• Ensure alignment with academic requirements.

• Approve scope during a scheduled team meeting.

• Final approval by Project Manager (Pushp).

## 6. Scope Control

• Any new idea must be reviewed and approved by the full team.

• All scope changes must be documented.

• Only the Project Manager can approve scope changes.

• No new deliverables will be added after Week 10.

# Cost Management Plan

## 1. Purpose of the Cost Plan

The purpose of this Cost Management Plan is to define how project costs will be estimated, budgeted, managed, and controlled to ensure the Smart Campus Energy Management System project stays within the approved academic budget and resource limits.

## 2. Cost Objectives

• Keep total project cost within the estimated $750 budget.

• Ensure all cost assumptions are realistic and justified.

• Track cost usage throughout the project.

• Document any changes in the cost baseline.

## 3. Cost Estimation Method

### A. Bottom-Up Estimating

Each task is estimated individually and then totaled. For example: estimated hours per team member multiplied by their academic hourly rate.

### B. Expert Judgment

Team members determine estimates based on academic expectations, workload, and reasonable assumptions.

### C. Analogous Estimating

Uses cost data from similar student projects as a reference point, adjusted based on current project scope.

## 4. Cost Breakdown (Budget Summary)

| COST TYPE | VENDOR / LABOR NAMES | RATE | QTY | AMOUNT |
| --- | --- | --- | --- | --- |
| Professional Cost (ex Development cost) | Data Visualization Lead | $60/hr | 20hrs | $1200 |
| Professional Cost | Energy Data Analyst | $45/hr | 10hrs | $450 |
| Professional Cost | Communication & Campaign Coordinator | $50/hr | 6 hrs | $300 |
| Professional Cost | Documentation & Report Writer | $30/hr | 5 hrs | $150 |
| Supplies | Open-source IoT dataset and Tableau (Student License) | Free | 1 | $0 |
| Miscellaneous | Printing awareness materials and posters | $1000 | 1 | $1000 |

TOTAL PROJECT COST: $3100

## 5. Cost Baseline

The approved cost baseline for this project is $3100. Any changes to the baseline must be documented and formally approved by the team.

## 6. Cost Control Process

### A. Weekly Cost Review

The team will compare actual hours worked against planned hours, track deviations, and update the cost tracker accordingly.

### B. Variance Tracking

The following formulas will be used to monitor and interpret cost performance:

• Cost Variance (CV) = Earned Value – Actual Cost

• Cost Performance Index (CPI) = Earned Value / Actual Cost

### C. Change Requests

If project costs need adjustment (e.g., increased printing costs), the full team must approve the change, and Pushp (PM) must record the update.

## 7. Reporting Costs

• Google Sheets cost tracker for ongoing cost updates.

• Weekly cost review during team meetings.

• Final cost summary included in the final project report.

## 8. Cost Assumptions

• All labor rates are academic estimates, not actual employment rates.

• All software is free under student licenses.

• No hardware purchases are needed for this project.

• Printing cost may vary slightly depending on usage.

• No additional hidden or unplanned expenses are expected.

# Resource Management Plan

## 1. Purpose of the Resource Plan

The purpose of this Resource Management Plan is to identify, assign, and manage all human resources, tools, and facilities required to successfully complete the Smart Campus Energy Management System project.

## 2. Project Team & Roles

| Team Member | Role | Responsibilities |
| --- | --- | --- |
| Pushp Chandrasinh Rathava | Project Manager / Data Analyst | Lead team, manage schedule, analyze data, approve deliverables |
| Dev Patel | Dashboard Developer / Data Visualization Lead | Build dashboards, clean data, create charts & insights |
| Sunny Sunny | Communication & Documentation Lead | Prepare all documents, manage communication, format reports |

## 3. RACI Matrix (Responsible, Accountable, Consulted, Informed)

| Task / Deliverable | Pushp | Dev | Sunny |
| --- | --- | --- | --- |
| Project Charter | A | C | R |
| Communication Plan | A | C | R |
| Risk Management Plan | A | C | R |
| Quality Management Plan | A | C | R |
| Scope Management Plan | A | C | R |
| Cost Management Plan | A | C | R |
| Resource Management Plan | A | C | R |
| Dataset Cleaning | R | R | I |
| Dashboard Development | C | A/R | I |
| Analysis & Insights | A/R | R | I |
| Educational Campaign | A | C | R |
| Final Report | A | C | R |
| Final Presentation | A | R | R |

Legend:

R = Responsible (does the work)

A = Accountable (final decision maker)

C = Consulted (provides input)

I = Informed (kept updated)

## 4. Required Tools & Resources

Software Tools:

• Tableau (Dashboard creation)

• Power BI (Backup option)

• Google Sheets / Excel (Datasets & calculations)

• Google Docs (Documentation)

• Google Slides / PowerPoint (Presentation)

• WhatsApp (Communication)

Hardware / Facilities:

• Laptops for each team member

• Internet access

• Computer Lab (if needed)

## 5. Resource Acquisition Plan

• All tools are free under student licenses.

• Team members provide their own laptops.

• Google Drive will be used for shared storage.

• No external contractors are needed.

## 6. Resource Training & Skill Requirements

| Resource | Required Skills | Training Needed? |
| --- | --- | --- |
| Pushp | Data analysis, Excel, project management | No |
| Dev | Tableau/Power BI, visualization, data cleaning | No (already skilled) |
| Sunny | Documentation, formatting, communication | No |

If needed, team members may use quick online tutorials for Tableau visuals.

## 7. Resource Monitoring & Control

• Weekly team check-ins to review workload and progress.

• Task progress tracked through Google Sheets.

• Project Manager adjusts assignments if workload imbalance occurs.

• High‑priority tasks may be reassigned if deadlines are at risk.

## 8. Resource Constraints

•  Limited time due to academic deadlines.

•  Team availability may vary due to classes and part-time work.

•  Only mock datasets can be used (no real IoT data access).

•  No access to real IoT sensors or campus energy systems.

# Work Breakdown Structure (WBS)

Smart Campus Energy Management System (SCEMS) Project

## LEVEL 1 – PROJECT

1.0 Smart Campus Energy Management System

## LEVEL 2 – MAIN PHASES

| WBS Code | Phase |
| --- | --- |
| 1.1 | Initiation |
| 1.2 | Planning |
| 1.3 | Execution |
| 1.4 | Monitoring & Controlling |
| 1.5 | Closing |

## LEVEL 3 – DETAILED WORK PACKAGES

### 1.1 Initiation

| WBS Code | Task |
| --- | --- |
| 1.1.1 | Form project team |
| 1.1.2 | Identify stakeholders |
| 1.1.3 | Define project purpose and scope |
| 1.1.4 | Develop project charter |
| 1.1.5 | Charter approval & sign-off |

### 1.2 Planning

| WBS Code | Task |
| --- | --- |
| 1.2.1 | Create Communication Plan |
| 1.2.2 | Create Risk Management Plan |
| 1.2.3 | Create Quality Management Plan |
| 1.2.4 | Create Scope Management Plan |
| 1.2.5 | Create Cost Management Plan |
| 1.2.6 | Create Resource Management Plan |
| 1.2.7 | Develop WBS |
| 1.2.8 | Create Project Schedule (Gantt Chart) |
| 1.2.9 | Review and approve planning documents |

### 1.3 Execution

| WBS Code | Task |
| --- | --- |
| 1.3.1 | Gather mock energy dataset |
| 1.3.2 | Clean dataset & prepare for analysis |
| 1.3.3 | Conduct energy analysis (patterns, peaks, trends) |
| 1.3.4 | Build Tableau/Power BI dashboards |
| 1.3.5 | Validate dashboard accuracy |
| 1.3.6 | Develop sustainability recommendations |
| 1.3.7 | Create educational awareness campaign materials |

### 1.4 Monitoring & Controlling

| WBS Code | Task |
| --- | --- |
| 1.4.1 | Hold weekly team meetings |
| 1.4.2 | Track progress against schedule |
| 1.4.3 | Update risk log |
| 1.4.4 | Ensure documentation quality |
| 1.4.5 | Dashboard review & correction |
| 1.4.6 | Version control for documents |

### 1.5 Closing

| WBS Code | Task |
| --- | --- |
| 1.5.1 | Prepare final project report |
| 1.5.2 | Prepare final presentation |
| 1.5.3 | Conduct final team review |
| 1.5.4 | Submit deliverables |
| 1.5.5 | Project closure & reflection |

# Project Schedule / Gantt Chart Plan

## 1.0 Initiation Phase (Oct 10 – Oct 18)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.1.1 | Form project team | Oct 10 – Oct 11 | 2 days |
| 1.1.2 | Identify stakeholders | Oct 11 – Oct 12 | 2 days |
| 1.1.3 | Define purpose & scope | Oct 12 – Oct 14 | 3 days |
| 1.1.4 | Develop project charter | Oct 14 – Oct 17 | 4 days |
| 1.1.5 | Review & approve charter | Oct 17 – Oct 18 | 2 days |

## 2.0 Planning Phase (Oct 19 – Nov 3)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.2.1 | Communication Plan | Oct 19 – Oct 21 | 3 days |
| 1.2.2 | Risk Management Plan | Oct 21 – Oct 23 | 3 days |
| 1.2.3 | Quality Management Plan | Oct 23 – Oct 24 | 2 days |
| 1.2.4 | Scope Management Plan | Oct 24 – Oct 26 | 3 days |
| 1.2.5 | Cost Management Plan | Oct 26 – Oct 27 | 2 days |
| 1.2.6 | Resource Management Plan | Oct 27 – Oct 29 | 3 days |
| 1.2.7 | WBS Development | Oct 29 – Oct 31 | 3 days |
| 1.2.8 | Create Project Schedule | Oct 31 – Nov 2 | 3 days |
| 1.2.9 | Planning Review & Approval | Nov 2 – Nov 3 | 2 days |

## 3.0 Execution Phase (Nov 4 – Dec 4)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.3.1 | Gather mock dataset | Nov 4 – Nov 6 | 3 days |
| 1.3.2 | Clean dataset | Nov 6 – Nov 10 | 5 days |
| 1.3.3 | Energy analysis | Nov 10 – Nov 14 | 5 days |
| 1.3.4 | Dashboard development | Nov 14 – Nov 23 | 10 days |
| 1.3.5 | Dashboard validation | Nov 23 – Nov 26 | 4 days |
| 1.3.6 | Sustainability recommendations | Nov 26 – Nov 30 | 5 days |
| 1.3.7 | Develop educational campaign | Nov 30 – Dec 4 | 5 days |

## 4.0 Monitoring & Controlling (Oct 10 – Dec 15)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.4.1 | Weekly meetings | Oct 10 – Dec 15 | Ongoing |
| 1.4.2 | Track progress | Oct 19 – Dec 15 | Ongoing |
| 1.4.3 | Update risk log | Oct 21 – Dec 15 | Ongoing |
| 1.4.4 | Documentation QA | Oct 21 – Dec 10 | Ongoing |
| 1.4.5 | Dashboard corrections | Nov 23 – Dec 10 | 18 days |
| 1.4.6 | Version control | Entire Project | Ongoing |

## 5.0 Closing Phase (Dec 4 – Dec 15)

| WBS | Task | Start – End | Duration |
| --- | --- | --- | --- |
| 1.5.1 | Final report | Dec 4 – Dec 10 | 7 days |
| 1.5.2 | Final presentation development | Dec 10 – Dec 13 | 4 days |
| 1.5.3 | Final team review | Dec 13 – Dec 14 | 2 days |
| 1.5.4 | Submission of project | Dec 15 – Dec 15 | 1 day |
| 1.5.5 | Project close-out reflection | Dec 15 – Dec 15 | 1 day |

# Solution Roadmap (Basecamp! Style)

Project: Smart Campus Energy Management System
Team: EcoVision

## 1. Strategic Themes

• Theme 1 — Improve Campus Energy Awareness: Use data and dashboards to educate students and staff.

• Theme 2 — Reduce Simulated Energy Consumption: Use analysis to highlight inefficiencies and propose improvements.

• Theme 3 — Enable Data-Driven Decisions: Provide clear dashboards and insights for decision-making.

• Theme 4 — Deliver High-Quality Academic Documentation: Ensure all project management documents meet expectations.

## 2. Epics

### Theme 1: Improve Campus Energy Awareness

• Epic 1.1: Educational Campaign

• Epic 1.2: Sustainability Recommendation Report

### Theme 2: Reduce Simulated Energy Consumption

• Epic 2.1: Dataset Collection & Cleaning

• Epic 2.2: Energy Usage Analysis

• Epic 2.3: ROI & Cost Savings Model

### Theme 3: Enable Data-Driven Decisions

• Epic 3.1: Dashboard Development (Tableau/Power BI)

• Epic 3.2: Dashboard Testing & Validation

• Epic 3.3: Insight Extraction

### Theme 4: Academic Documentation

• Epic 4.1: Project Management Plans

• Epic 4.2: Project Report

• Epic 4.3: Final Presentation

## 3. Features (Detailed Work Items Under Each Epic)

### Epic 2.1 — Dataset Collection & Cleaning

• F2.1.1 Collect mock IoT energy dataset

• F2.1.2 Standardize units (kWh, costs)

• F2.1.3 Remove duplicates & missing values

• F2.1.4 Validate structure for Tableau

### Epic 2.2 — Energy Usage Analysis

• F2.2.1 Identify daily & weekly usage patterns

• F2.2.2 Calculate peak load hours

• F2.2.3 Analyze cost per time period

• F2.2.4 Estimate potential savings

### Epic 3.1 — Dashboard Development

• F3.1.1 Create energy consumption dashboard

• F3.1.2 Create cost visualization dashboard

• F3.1.3 Create peak load & trend dashboard

• F3.1.4 Add KPIs (Total kWh, Peak Time, Cost)

### Epic 3.2 — Dashboard Validation

• F3.2.1 Data accuracy check

• F3.2.2 Visual clarity testing

• F3.2.3 Peer feedback & correction

### Epic 1.1 — Educational Campaign

• F1.1.1 Create sustainability posters

• F1.1.2 Create awareness messages

• F1.1.3 Create recommended best practices list

### Epic 4.1 — Documentation

• F4.1.1 Stakeholder Register

• F4.1.2 Communication Plan

• F4.1.3 Risk Plan

• F4.1.4 Quality Plan

• F4.1.5 Scope Plan

• F4.1.6 Cost Plan

• F4.1.7 Resource Plan

• F4.1.8 WBS

• F4.1.9 Schedule

### Epic 4.2 — Final Report

• F4.2.1 Write summary

• F4.2.2 Add dashboard screenshots

• F4.2.3 Add insights & recommendations

• F4.2.4 Format & finalize

### Epic 4.3 — Final Presentation

• F4.3.1 Slide design

• F4.3.2 Add dashboards

• F4.3.3 Add speaker notes

• F4.3.4 Practice & finalize

## 4. Timeline / Release Plan (Aha! View)

### Release 1 — Project Foundation (Oct 10 – Oct 18)

• Stakeholder identification

• Project Charter

• Team formation

### Release 2 — Full Documentation (Oct 19 – Nov 3)

• Communication, Risk, Quality, Scope, Cost, Resource Plans

• WBS

• Schedule

### Release 3 — Data & Dashboard Build (Nov 4 – Dec 4)

• Dataset cleaning

• Analysis

• Dashboard creation

• Dashboard testing

• Sustainability suggestions

• Educational campaign

### Release 4 — Final Delivery (Dec 4 – Dec 15)

• Final report

• Final presentation

• Project submission

• Closure